INTRODUCTION TO PROJECT MANAGEMENT

LEARNING MATERIAL CREATION

Module: Work Breakdown Structure (WBS), 100% Rule & Critical Path Method (CPM)

# 1. Module Design and Alignment

This module is designed as an online learning experience rather than a conventional set of lecture notes. Learners first acquire the concepts, then practice them through guided interactions, apply them to authentic project cases, and finally demonstrate understanding through formative assessment with immediate explanatory feedback.

## 1.1 Learning Objectives

LO1 — Develop a hierarchical Work Breakdown Structure (WBS) and apply the 100% Rule to verify scope completeness.

LO2 — Identify activities, predecessors, durations and basic dependency relationships and construct a precedence network.

LO3 — Perform a basic forward pass and backward pass, calculate total float, and identify the critical path using CPM.

LO4 — Apply WBS and scheduling concepts to realistic project-management decisions involving scope, constraints, risk and schedule compression.

## 1.2 Learning-Objective Alignment Map

| Learning Objective | Content | Interactive Activity | Formative Evidence |
| --- | --- | --- | --- |
| LO1 | WBS, decomposition, work packages, 100% Rule, WBS Dictionary | WBS Builder + Spot-the-Mistake | WBS task + MCQs |
| LO2 | Activities, predecessors, FS/SS/FF, precedence networks | Dependency Matching + Network Builder | Scenario questions |
| LO3 | ES, EF, LS, LF, float, critical path | CPM Calculation Challenge | Numerical problems |
| LO4 | AstraZeneca and Mayo Clinic cases; trade-offs | Case Decision Labs | Case-based questions |

## 1.3 Learner Journey

| Stage | Learner action | Approx. time |
| --- | --- | --- |
| 1. Learn | Read concept explanations and examples | 25 min |
| 2. Practice | Complete guided WBS and dependency activities | 25 min |
| 3. Apply | Solve CPM and real-world case challenges | 35 min |
| 4. Check | Complete formative assessment and feedback | 20 min |
| 5. Reflect | Complete exit ticket/self-check | 5 min |

# 2. Learning Content A — WBS and the 100% Rule

## 2.1 What is a WBS?

A Work Breakdown Structure is a hierarchical decomposition of the project's total scope into smaller, manageable components. PMI describes the WBS as a deliverable-oriented structure that captures the project's work and provides a foundation for planning, estimating, scheduling and control. The WBS may be represented graphically, textually or in a table.

Source note: PMI emphasizes decomposition, completeness, appropriate detail and the 100% Rule. citeturn0search1turn0search3

## 2.2 The 100% Rule

The 100% Rule means the WBS must contain all work required by the approved project scope—nothing essential omitted and no out-of-scope work added. The child elements at each level should collectively represent the full work of their parent. Project-management work is included when it is part of the project scope. citeturn0search1turn0search62

## 2.3 WBS Quality Checklist

Deliverable-oriented rather than simply a chronological to-do list.

All required project work is represented.

Child elements collectively represent the parent element.

Elements do not unnecessarily overlap.

Decomposition stops at a level that is manageable and useful.

Work packages can be estimated, assigned and monitored.

A coding scheme makes the hierarchy easy to navigate.

## 2.4 Three Practical WBS Examples

Example A — Enterprise Software Implementation

| Code | Element |
| --- | --- |
| 1.0 | Enterprise Software Implementation |
| 1.1 | Governance and Project Management |
| 1.1.1 | Project Charter and Governance |
| 1.1.2 | Stakeholder Reporting |
| 1.2 | Requirements and Architecture |
| 1.2.1 | Business Workflow Definition |
| 1.2.2 | Database Architecture |
| 1.3 | Development and Testing |
| 1.3.1 | System Integration |
| 1.3.2 | User Acceptance Testing |
| 1.4 | Deployment and Handover |
| 1.4.1 | Production Cutover |
| 1.4.2 | End-User Training |

Example B — College Technical Fest

| Code | Element |
| --- | --- |
| 1.0 | College Technical Fest |
| 1.1 | Planning and Governance |
| 1.1.1 | Budget and Approval |
| 1.1.2 | Venue and Permissions |
| 1.2 | Marketing and Registration |
| 1.2.1 | Campaign |
| 1.2.2 | Registration System |
| 1.3 | Event Operations |
| 1.3.1 | Stage and Technical Setup |
| 1.3.2 | Volunteer Coordination |
| 1.4 | Closure |
| 1.4.1 | Financial Closure |
| 1.4.2 | Feedback and Lessons Learned |

Example C — Healthcare Expansion (conceptual learning model)

| Major deliverable | Possible decomposition |
| --- | --- |
| Facility Expansion | New floors; patient areas; mechanical systems |
| Technology Integration | Bedside technology; displays; AI-assisted capabilities |
| Clinical/Operational Readiness | Staff readiness; workflows; patient experience |
| Data and EHR Integration | EHR-connected systems; data fidelity; testing |
| Governance and Risk | Go/no-go decisions; risk review; change control |

The healthcare example is informed by PMI's Mayo Clinic case, which describes five new floors, advanced bedside technology, AI-assisted capabilities, EHR integration and safety-focused governance. citeturn0search0

## 2.5 WBS Dictionary — Worked Example

A WBS Dictionary adds the detail needed to understand and control each WBS element. ProjectManagementDocs provides practical WBS and dictionary templates that illustrate definitions, deliverables, resources and related planning information. citeturn1search0turn1search1

| WBS Code | Work Package | Definition | Acceptance Criteria | Responsible |
| --- | --- | --- | --- | --- |
| 1.3.2 | User Acceptance Testing | Test the configured system against approved user requirements. | Critical defects resolved; business users sign off. | QA / Business Team |
| 1.4.1 | Production Cutover | Move the approved system into the live environment. | System operational and validated. | IT Team |
| 1.4.2 | End-User Training | Prepare users to operate the new system. | Target users complete training. | Training Lead |

# 3. Interactive Learning Lab A — WBS

## Activity A1: Build the WBS

Scenario: Your university is launching a new Learning Management System (LMS). The project must cover requirements, configuration, data migration, testing, training, deployment, governance and handover.

Create five Level-2 deliverables under the project.

Break at least three deliverables into Level-3 work packages.

Use nouns or deliverable-oriented terms rather than a sequence of actions.

Check the WBS against the 100% Rule.

Mark one item that is intentionally out of scope.

### Self-check feedback

A strong answer should include governance/project management, requirements, technical configuration, data migration, testing, training, deployment and closure/handover. If one of these is essential to the approved scope but absent, the WBS is incomplete.

## Activity A2: Spot the WBS Mistakes

Review this deliberately flawed WBS:

| Item | Learner decision |
| --- | --- |
| 1.0 Mobile App Project | Keep / Change |
| 1.1 Write code | Keep / Change |
| 1.2 Test app | Keep / Change |
| 1.3 Hire developers | Keep / Change |
| 1.4 Make coffee | Keep / Change |
| 1.5 Launch app | Keep / Change |
| 1.6 Fix bugs | Keep / Change |

Identify at least three problems.

Rewrite two elements so they are deliverable-oriented.

Identify the clearly out-of-scope item.

Explain whether the WBS is complete enough to represent the full project scope.

Feedback: The exercise is designed to distinguish scope/deliverables from individual activities, resources and irrelevant work. PMI notes that effective WBS structures are deliverable-oriented and should represent 100% of scope. citeturn0search5turn0search8

## Activity A3: Case Decision — Mayo Clinic Expansion

PMI's Mayo Clinic case describes a major expansion in Jacksonville involving five new floors, technology deployment, EHR-connected systems, AI-assisted capabilities, patient safety requirements and governance. The team used a waterfall construction timeline with iterative technology development and go/no-go decisions that prioritized safety. citeturn0search0

Choose five Level-2 WBS branches for this project.

Identify two deliverables that are not construction work but are essential to successful activation.

Explain why patient safety should be treated as a project constraint rather than an optional feature.

Suggest one work package for technology testing and one for staff readiness.

Debrief: A strong response recognizes that the project outcome depends on more than physical construction. Technology, EHR fidelity, staff readiness, governance and patient safety are integral to the project's scope and delivery conditions. citeturn0search0

# 4. Learning Content B — Dependencies and CPM

## 4.1 From WBS to Schedule

The WBS answers WHAT must be delivered. The schedule translates the work into activities and answers WHEN the work can occur. Network logic then describes HOW activities depend on one another. MIT OpenCourseWare's project-management materials explicitly connect planning with WBS, scheduling and CPM/PDM methods. citeturn1search2

## 4.2 Dependency Types

| Relationship | Meaning | Simple example |
| --- | --- | --- |
| Finish-to-Start (FS) | Successor starts after predecessor finishes. | Testing starts after development finishes. |
| Start-to-Start (SS) | Successor starts after predecessor starts. | Marketing can begin after product development starts. |
| Finish-to-Finish (FF) | Successor finishes after predecessor finishes. | Documentation finishes when the final system build is completed. |

## 4.3 CPM Core Terms and Formulas

| Term | Meaning / Formula |
| --- | --- |
| ES | Earliest Start |
| EF | Earliest Finish = ES + Duration |
| LS | Latest Start = LF − Duration |
| LF | Latest Finish |
| Total Float | TF = LS − ES = LF − EF |
| Critical Path | Longest path through the network; activities normally have zero float in the basic CPM model. |

## 4.4 Visual Network Example

Use the following network to understand the logic before calculating:

A (3) → B (4) → D (6) → E (3)
   ↘ C (2) ───────────────↗

The path A–B–D–E has duration 3+4+6+3 = 16. The alternative A–C–E has duration 3+2+3 = 8. Therefore A–B–D–E is the critical path for this example.

## 4.5 CPM Worked Example

| Activity | Pred. | Dur. | ES | EF | LS | LF | TF | Critical |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | — | 3 | 0 | 3 | 0 | 3 | 0 | Yes |
| B | A | 4 | 3 | 7 | 3 | 7 | 0 | Yes |
| C | A | 2 | 3 | 5 | 7 | 9 | 4 | No |
| D | B | 6 | 7 | 13 | 7 | 13 | 0 | Yes |
| E | C,D | 3 | 13 | 16 | 13 | 16 | 0 | Yes |

Interpretation: project duration = 16 time units; critical path = A–B–D–E; C has 4 time units of total float.

For additional authentic CPM practice, MIT OpenCourseWare provides a project-management problem set with precedence relations, activity durations and critical-path scheduling calculations. citeturn1search10

# 5. Interactive Learning Lab B — CPM

## Activity B1: Dependency Matching

| Situation | Choose |
| --- | --- |
| Testing begins only after development is complete. | FS / SS / FF |
| Marketing begins once development starts. | FS / SS / FF |
| Documentation and final system build must finish together. | FS / SS / FF |

Feedback: Expected answers are FS, SS and FF respectively. The purpose is to make learners identify logic before calculating dates.

## Activity B2: CPM Challenge

Solve without looking at the worked answer. Activities:

| Activity | Predecessor | Duration |
| --- | --- | --- |
| A | — | 4 |
| B | A | 3 |
| C | A | 5 |
| D | B | 2 |
| E | C,D | 3 |

Draw the precedence network.

Calculate ES and EF.

Calculate LS and LF using a backward pass.

Calculate total float.

Identify the critical path and total project duration.

Self-check answer: A–C–E is the critical path and the project duration is 12 time units. B and D form a shorter parallel branch.

## Activity B3: Delay Simulation

Return to the original A–B–D–E example.

If C is delayed by 3 time units, does the project completion date change?

If C is delayed by 5 time units, what happens?

If D is delayed by 2 time units, what happens?

Explain why the same amount of delay can have different project-level consequences.

Feedback: C has 4 units of float, so a 3-unit delay can be absorbed in the original model. A 5-unit delay exceeds its float and would push the project finish by 1 unit. D is critical, so a 2-unit delay threatens the project finish by 2 units unless corrective action changes the network or duration.

# 6. Real-World Application Lab

## 6.1 Case Study — AstraZeneca: Fighting a Global Pandemic

PMI's case study reports that AstraZeneca worked with the University of Oxford while managing clinical trials and simultaneously ramping up manufacturing capacity. The project also had to address differing regulatory and compliance requirements across government customers. PMI identifies the accelerated timeline, complexity, risk and need for strong project-management infrastructure as central features of the case. citeturn0search2turn0search61

### Case Decision Lab: You Are the Project Manager

Which activities might be candidates for parallel work, and which dependencies should remain protected?

Which activities could become critical because the schedule has been compressed?

What new risks appear when activities that were traditionally sequential are overlapped?

How could regulatory requirements create additional dependencies?

Write a 3–4 sentence recommendation for the project sponsor.

Model reasoning: Speed can require parallel work, but safety, regulatory and technical dependencies cannot simply be ignored. The project manager must identify which activities can overlap without invalidating required controls, then monitor the resulting risks closely. PMI's case emphasizes the simultaneous management of clinical trials and manufacturing capacity plus multiple regulatory frameworks. citeturn0search2turn0search61

## 6.2 Case Study — Mayo Clinic Expansion

PMI reports that Mayo Clinic expanded a Jacksonville facility by five floors while introducing advanced bedside technology and AI-assisted capabilities. The project combined a waterfall construction schedule with iterative technology development, used pilots and mockups, and employed go/no-go decisions that prioritized patient safety. citeturn0search0

### Case Challenge

Create five Level-2 WBS elements.

Identify one scope item, one schedule dependency, one stakeholder requirement and one risk.

Explain how a last-minute technology change could affect scope, schedule and procurement.

Propose a go/no-go checkpoint before activation.

## 6.3 Relatable Application — College Technical Fest

Use the same project-management logic in a familiar context.

Create a WBS for a one-day technical fest.

Identify three dependencies between event activities.

Estimate durations for five activities.

Determine which sequence is likely to control the event-readiness date.

Identify one scope-creep request and explain how you would handle it.

# 7. Online-Course Usability Features

## 7.1 Microlearning Structure

Content is intentionally divided into short learning chunks. Each concept is followed by a practice prompt so that learners do not have to read the entire module before applying it.

| Learning screen/section | Learner interaction |
| --- | --- |
| Concept card | Read definition + one example |
| Check Your Understanding | Answer one quick question |
| Try It | Complete a small WBS or CPM step |
| Feedback | Compare reasoning with an explanation |
| Case Lab | Make a project decision |
| Assessment | Demonstrate independent understanding |

## 7.2 Accessibility and Clarity

Use short paragraphs and descriptive headings.

Do not rely on colour alone to communicate critical/non-critical status.

Present tables with clear headers.

Provide textual descriptions alongside diagrams.

Use consistent terminology and formulas throughout.

Keep instructions action-oriented: Identify, calculate, compare, justify.

## 7.3 Learner Feedback Design

Every formative item should provide a reason, not just a correct answer. Suggested feedback pattern:

| Response | Feedback |
| --- | --- |
| Correct | Confirm the concept and explain why it is correct. |
| Incorrect | Identify the misconception and point the learner back to the relevant rule. |
| Calculation error | Show which step should be checked without immediately revealing every step. |
| Strong case answer | Identify the project-management principle demonstrated. |

# 8. Formative Assessment Bank

## 8.1 Multiple Choice

1. Which statement best describes the 100% Rule?

A. The WBS must contain exactly 100 work packages.

B. The WBS must capture all work within approved scope and no extra work.

C. Every activity must have 100% float.

D. The project must be completed in 100 days.

Answer: B

Feedback: Correct: The 100% Rule requires the WBS to represent the full approved scope. Incorrect: the rule is about scope completeness, not the number of activities, float or project duration.

2. Which relationship means a successor starts after its predecessor finishes?

A. SS

B. FF

C. FS

D. SF

Answer: C

Feedback: Correct: Finish-to-Start means the predecessor finishes before the successor starts.

3. In the worked CPM example, which activity has 4 units of float?

A. A

B. B

C. C

D. D

Answer: C

Feedback: Correct: C has ES 3, LS 7, giving 4 units of total float.

4. Which is the critical path in the worked example?

A. A–C–E

B. A–B–D–E

C. B–D

D. C–E

Answer: B

Feedback: Correct: A–B–D–E is the longest path at 16 time units.

5. Which is the best response to a major scope change request?

A. Add it immediately.

B. Ignore it.

C. Assess impact and use the approved change-control process.

D. Remove an unrelated deliverable.

Answer: C

Feedback: Correct: Scope changes should be assessed and controlled rather than informally added.

## 8.2 Scenario-Based Questions

Activity C has 4 units of float and is delayed by 3 units. Should the project completion date change? Explain.

A stakeholder asks the team to add a new feature during development. What information should the project manager assess before accepting the change?

A project team wants to fast-track two activities. What three questions should be asked before approving the overlap?

Why could the WBS be considered a foundation for both scheduling and cost estimation?

## 8.3 Performance Task

Create a one-page WBS and a simple precedence network for a college technical fest. Submit: (1) WBS, (2) five activity durations, (3) dependencies, (4) critical-path calculation, and (5) a 100-word explanation of one project risk.

### Performance Rubric

| Criterion | 4 — Excellent | 3 — Good | 2 — Developing | 1 — Beginning |
| --- | --- | --- | --- | --- |
| WBS completeness | Full scope and clear hierarchy | Minor omission | Several omissions | Major scope missing |
| 100% Rule | Correctly justified | Mostly correct | Partial justification | Not demonstrated |
| Network/CPM | Correct logic and calculations | Minor error | Multiple errors | Network unclear |
| Real-world reasoning | Strong, evidence-based trade-off | Relevant reasoning | Basic reasoning | Unsupported |
| Communication | Clear and learner-friendly | Mostly clear | Some ambiguity | Difficult to follow |

# 9. Module Summary and Exit Ticket

WBS answers WHAT work is in scope.

100% Rule checks that all approved project work is represented.

Dependencies describe logical relationships between activities.

CPM identifies the sequence that controls minimum project duration.

Float measures schedule flexibility.

Real projects require trade-offs between time, scope, risk, quality, resources and constraints.

Exit ticket — complete in one minute:

One concept I can explain is…

One calculation I can now perform is…

One project-management decision I would handle differently after this module is…

# 10. Glossary

| Term | Definition |
| --- | --- |
| WBS | Hierarchical decomposition of the project's approved scope. |
| 100% Rule | Principle that the WBS captures all work in scope and no out-of-scope work. |
| Work Package | A manageable lowest-level WBS component suitable for planning and control. |
| WBS Dictionary | Supporting document that defines WBS elements and their details. |
| Predecessor | Activity that logically precedes another activity. |
| Dependency | Logical relationship between project activities. |
| Critical Path | Longest-duration path through the network in basic CPM. |
| Total Float | Scheduling flexibility before an activity delays the project finish. |
| Fast-Tracking | Overlapping activities that were planned sequentially, where feasible. |
| Scope Creep | Uncontrolled expansion of project scope without appropriate change control. |

# 11. Source Quality and Further Learning

The module prioritizes authoritative or directly useful sources. Primary/standards-oriented PMI material is used for WBS principles and real project cases; MIT OpenCourseWare is used for academic CPM practice; ProjectManagementDocs is used as a practical template repository.

| Source | URL | Used for |
| --- | --- | --- |
| PMI — Building high quality work breakdown structures | https://www.pmi.org/learning/library/practice-standard-work-breakdown-structures-8063 | WBS definition, decomposition, 100% Rule and quality principles. |
| PMI — Developing and elaborating effective WBS | https://www.pmi.org/learning/library/developing-elaborating-work-breakdown-structures-7241 | 100% Rule, WBS representations and relationship to scheduling. |
| PMI — AstraZeneca: Fighting a Global Pandemic | https://www.pmi.org/es-419/business-solutions/case-studies/astrazeneca-case-study | Authentic case on clinical trials, manufacturing, regulatory complexity and project infrastructure. |
| PMI — Mayo Clinic Expansion | https://www.pmi.org/business-solutions/case-studies/mayo-clinic | Authentic case on hospital expansion, technology, EHR, safety, governance and hybrid delivery. |
| MIT OpenCourseWare — Project Management Problem Set | https://ocw.mit.edu/courses/1-204-computer-algorithms-in-systems-engineering-spring-2010/b5a50a9181b97500e8d6d05bef481e24_MIT1_204S10_assn5.pdf | Academic CPM problem set with precedence relations, durations and critical-path calculations. |
| MIT OpenCourseWare — Project Management syllabus | https://ocw.mit.edu/courses/1-040-project-management-spring-2004/pages/syllabus/ | Academic overview connecting WBS, scheduling, CPM and PDM. |
| ProjectManagementDocs — WBS Template | https://www.projectmanagementdocs.com/template/project-planning/work-breakdown-structure/ | Practical WBS layouts, WBS Dictionary example and glossary. |
| ProjectManagementDocs — Scope Management Plan | https://www.projectmanagementdocs.com/template/project-planning/scope-management-plan/ | WBS Dictionary and scope-control template material. |

Academic-use note: Source material is paraphrased in this module. Any external figures, screenshots or verbatim quotations should be reproduced only when the source's reuse terms permit it and should be attributed appropriately.

# 12. Facilitator / Instructor Notes

Use Activity A1 before showing the model WBS so learners generate an initial structure independently.

During Activity A2, ask learners to explain why each item is a WBS element, activity, resource or out-of-scope item.

For CPM, require learners to draw the network before showing ES/EF/LS/LF calculations.

Use the AstraZeneca case for schedule-compression reasoning rather than asking learners to reproduce factual details.

Use the Mayo Clinic case for scope completeness, governance, risk and technology integration.

Allow learners to retry formative questions after reading the feedback.

Use the final performance task as the module-level evidence of achievement.